## Index
PROJECT MANAGEMENT TEMPLATE LIBRARY
Reusable PM control templates - RAID, registers, logs, WBS, Kanban, status reporting
# | Template | Purpose
1 | RAID Log | Consolidated Risks, Assumptions, Issues, Dependencies
2 | Risk Register | Detailed risk scoring with auto P×I severity
3 | Issue Log | Live issue tracking with priority & ownership
4 | Stakeholder Register | Power/interest mapping & engagement strategy
5 | RACI Matrix | Responsibility assignment across deliverables
6 | Lessons Learned | Capture & categorise project learnings
7 | Action Log | Action item tracking with due dates & status
8 | Decision Log | Record key decisions & rationale
9 | Change Log | Change request control with impact assessment
10 | WBS | Work Breakdown Structure with phases & packages
11 | Milestone Tracker | Milestone schedule with RAG status
12 | Kanban Board | Backlog / To Do / In Progress / Review / Done
13 | Status Report | Weekly/period project status summary

## RAID Log
RAID Log
Type = Risk / Assumption / Issue / Dependency. One consolidated control log.
ID | Type | Description | Impact | Owner | Date Raised | Target Date | Status | Mitigation / Action
RAID-001 | Risk | Vendor delivery slippage on power equipment | High | PM | 2023-07-03 | 2023-07-31 | Open | Weekly vendor checkpoint; dual-source critical items
RAID-002 | Dependency | Site readiness required before equipment install | High | Ops Lead | 2023-07-05 | 2023-07-20 | Open | Track site-ready date in milestone tracker
RAID-003 | Assumption | Permits granted within 14 days of submission | Medium | PMO | 2023-07-01 | - | Open | Validate with regulatory team

## Risk Register
Risk Register
Severity auto-calculates as Probability × Impact (1-5 scale). Score ≥15 = Critical.
Risk ID | Risk Description | Category | Probability (1-5) | Impact (1-5) | Severity (P×I) | Severity Band | Owner | Response Strategy | Mitigation Actions | Status
R-001 | Vendor delivery slippage | Schedule | 4 | 4 |  |  | PM | Mitigate | Dual-source; weekly checkpoints | Open
R-002 | Budget overrun on civil works | Cost | 3 | 4 |  |  | Finance | Mitigate | Lock unit rates in contract | Open
R-003 | Tower-climb safety incident | HSE | 2 | 5 |  |  | EHS Lead | Mitigate | Mandatory training; PPE audits | Open

## Issue Log
Issue Log
Active issues (problems that have already occurred). Track priority, owner, resolution.
Issue ID | Description | Priority | Raised By | Date Raised | Owner | Status | Resolution / Next Step | Date Resolved
I-001 | Equipment delivered to wrong site | High | Site Eng | 2023-07-10 | Logistics | Open | Re-route to correct site; confirm GPS | -
I-002 | Splicing delay awaiting OTDR result | Medium | Fiber Lead | 2023-07-12 | Vendor | In Progress | Escalate to vendor PM | -

## Stakeholder Register
Stakeholder Register
Power/Interest grid drives engagement strategy. Quadrant auto-suggests approach.
ID | Stakeholder / Role | Organisation | Power (1-5) | Interest (1-5) | Quadrant Strategy | Engagement Approach | Comms Frequency | Owner
S-001 | Programme Sponsor | [Organization] | 5 | 5 |  | Manage Closely - co-decision | Weekly | PM
S-002 | Regulatory Body | Government | 4 | 2 |  | Keep Satisfied - formal updates | Monthly | PMO
S-003 | Field Technicians | [Vendor] | 2 | 4 |  | Keep Informed - briefings | Weekly | Ops Lead

## RACI Matrix
RACI Matrix
R=Responsible A=Accountable C=Consulted I=Informed. One A per row.
Deliverable / Activity | Project Manager | Sponsor | Ops Lead | EHS Lead | Vendor | Finance | PMO
Project charter approval | R | A | C | I | I | C | C
Site readiness sign-off | A | I | R | C | C | I | I
Risk register maintenance | A | I | C | C | I | I | R
Vendor contract award | C | A | I | I | R | R | C

## Lessons Learned
Lessons Learned
Capture what worked / what didn't. Category + recommendation for future projects.
ID | Project Phase | Category | What Happened | Impact | Lesson / Root Cause | Recommendation | Owner
LL-001 | Delivery | Vendor Mgmt | Single-source vendor delayed power kit | Schedule +2 wks | Over-reliance on one supplier | Pre-qualify 2+ vendors for critical items | PMO
LL-002 | Planning | Scheduling | Site-readiness not gated before install | Rework on 4 sites | Missing dependency gate | Add readiness gate to milestone plan | PM

## Action Log
Action Log
Action items from meetings. Overdue flag auto-triggers when past due & not done.
Action ID | Action Description | Owner | Date Raised | Due Date | Status | Overdue? | Notes
A-001 | Confirm OTDR results with vendor | Fiber Lead | 2023-07-17 | 2023-07-21 | Open |  | Awaiting vendor
A-002 | Submit capitalization WSR | PM | 2023-07-01 | 2023-07-05 | Done |  | Submitted
Formulas:
Overdue? = IF(AND([Status]<>"Done",[Status]<>"",ISNUMBER([Due Date]),[Due Date]<TODAY()),"OVERDUE","")

## Decision Log
Decision Log
Record key decisions, who made them, alternatives considered, and rationale.
ID | Decision | Date | Decision Maker | Alternatives Considered | Rationale | Impact
D-001 | Dual-source power equipment | 2023-07-04 | Sponsor | Single-source (cheaper) | De-risk delivery slippage | +5% cost, -2wk risk

## Change Log
Change Log
Change control. Each request assessed for scope/cost/schedule impact before approval.
CR ID | Change Description | Requested By | Date | Scope Impact | Cost Impact | Schedule Impact | Status | Approver
CR-001 | Add 12 sites to retrofit scope | Ops Lead | 2023-08-01 | +12 sites | +£X | +1 week | Pending | Sponsor

## WBS
WBS
Work Breakdown Structure. Decompose project into phases → packages → tasks.
WBS # | Level | Phase / Package / Task | Owner | Start | Finish | % Complete | Dependencies
1 | Phase | Initiation | PM | 2023-06-01 | 2023-06-15 | 100%
1.1 | Package | Project charter | PM | 2023-06-01 | 2023-06-07 | 100% | -
1.2 | Package | Stakeholder analysis | PMO | 2023-06-08 | 2023-06-15 | 100% | 1.1
2 | Phase | Planning | PM | 2023-06-16 | 2023-07-15 | 80% | 1
2.1 | Package | WBS & schedule | PM | 2023-06-16 | 2023-06-30 | 100% | 1
2.2 | Package | Risk & RAID baseline | PMO | 2023-07-01 | 2023-07-15 | 60% | 2.1
3 | Phase | Delivery | Ops Lead | 2023-07-16 | 2023-09-30 | 45% | 2
3.1 | Package | Site builds | Ops Lead | 2023-07-16 | 2023-09-15 | 50% | 2.2
3.2 | Package | Power & energy install | Vendor | 2023-08-01 | 2023-09-30 | 40% | 3.1
4 | Phase | Closure | PM | 2023-10-01 | 2023-10-15 | 0% | 3

## Milestone Tracker
Milestone Tracker
Key milestones with RAG. Variance auto-calculates Baseline vs Forecast (days).
Milestone | Baseline Date | Forecast/Actual Date | Variance (days) | RAG | Owner | Comments
Charter approved | 2023-06-15 | 2023-06-15 |  | Green | PM | On time
Planning complete | 2023-07-15 | 2023-07-20 |  | Amber | PM | 5-day slip
50% sites delivered | 2023-08-31 | 2023-09-10 |  | Red | Ops | Vendor delay

## Kanban Board
Kanban Board
Move cards across columns. Use one row per task; fill the relevant column.
Backlog | To Do | In Progress | Review | Done
Add new sites | Order power kit | Splice 63 sites | QA retrofit | Charter signed
Q4 budget plan | Vendor PQ | Civil works | OTDR review | Stakeholder map

## Status Report
PROJECT STATUS REPORT
Project Name
Project Manager
Reporting Period
Overall RAG | Green / Amber / Red
Schedule RAG
Budget RAG
Scope RAG
Risk RAG
Key Achievements This Period
•
•
•
Planned for Next Period
•
•
•
Key Risks & Issues
•
•
•
Decisions / Escalations Needed
•
•
•