## Issue Log
Issue Log
Active issues (problems that have already occurred). Track priority, owner, resolution.
Issue ID | Description | Priority | Raised By | Date Raised | Owner | Status | Resolution / Next Step | Date Resolved
I-001 | Equipment delivered to wrong site | High | Site Eng | 2023-07-10 | Logistics | Open | Re-route to correct site; confirm GPS | -
I-002 | Splicing delay awaiting OTDR result | Medium | Fiber Lead | 2023-07-12 | Vendor | In Progress | Escalate to vendor PM | -