## Lessons Learned
Lessons Learned
Capture what worked / what didn't. Category + recommendation for future projects.
ID | Project Phase | Category | What Happened | Impact | Lesson / Root Cause | Recommendation | Owner
LL-001 | Delivery | Vendor Mgmt | Single-source vendor delayed power kit | Schedule +2 wks | Over-reliance on one supplier | Pre-qualify 2+ vendors for critical items | PMO
LL-002 | Planning | Scheduling | Site-readiness not gated before install | Rework on 4 sites | Missing dependency gate | Add readiness gate to milestone plan | PM