## Milestone Tracker
Milestone Tracker
Key milestones with RAG. Variance auto-calculates Baseline vs Forecast (days).
Milestone | Baseline Date | Forecast/Actual Date | Variance (days) | RAG | Owner | Comments
Charter approved | 2023-06-15 | 2023-06-15 |  | Green | PM | On time
Planning complete | 2023-07-15 | 2023-07-20 |  | Amber | PM | 5-day slip
50% sites delivered | 2023-08-31 | 2023-09-10 |  | Red | Ops | Vendor delay