## RAID Log
RAID Log
Type = Risk / Assumption / Issue / Dependency. One consolidated control log.
ID | Type | Description | Impact | Owner | Date Raised | Target Date | Status | Mitigation / Action
RAID-001 | Risk | Vendor delivery slippage on power equipment | High | PM | 2023-07-03 | 2023-07-31 | Open | Weekly vendor checkpoint; dual-source critical items
RAID-002 | Dependency | Site readiness required before equipment install | High | Ops Lead | 2023-07-05 | 2023-07-20 | Open | Track site-ready date in milestone tracker
RAID-003 | Assumption | Permits granted within 14 days of submission | Medium | PMO | 2023-07-01 | - | Open | Validate with regulatory team