## Risk Register
Risk Register
Severity auto-calculates as Probability × Impact (1-5 scale). Score ≥15 = Critical.
Risk ID | Risk Description | Category | Probability (1-5) | Impact (1-5) | Severity (P×I) | Severity Band | Owner | Response Strategy | Mitigation Actions | Status
R-001 | Vendor delivery slippage | Schedule | 4 | 4 |  |  | PM | Mitigate | Dual-source; weekly checkpoints | Open
R-002 | Budget overrun on civil works | Cost | 3 | 4 |  |  | Finance | Mitigate | Lock unit rates in contract | Open
R-003 | Tower-climb safety incident | HSE | 2 | 5 |  |  | EHS Lead | Mitigate | Mandatory training; PPE audits | Open