## WBS
WBS
Work Breakdown Structure. Decompose project into phases → packages → tasks.
WBS # | Level | Phase / Package / Task | Owner | Start | Finish | % Complete | Dependencies
1 | Phase | Initiation | PM | 2023-06-01 | 2023-06-15 | 100%
1.1 | Package | Project charter | PM | 2023-06-01 | 2023-06-07 | 100% | -
1.2 | Package | Stakeholder analysis | PMO | 2023-06-08 | 2023-06-15 | 100% | 1.1
2 | Phase | Planning | PM | 2023-06-16 | 2023-07-15 | 80% | 1
2.1 | Package | WBS & schedule | PM | 2023-06-16 | 2023-06-30 | 100% | 1
2.2 | Package | Risk & RAID baseline | PMO | 2023-07-01 | 2023-07-15 | 60% | 2.1
3 | Phase | Delivery | Ops Lead | 2023-07-16 | 2023-09-30 | 45% | 2
3.1 | Package | Site builds | Ops Lead | 2023-07-16 | 2023-09-15 | 50% | 2.2
3.2 | Package | Power & energy install | Vendor | 2023-08-01 | 2023-09-30 | 40% | 3.1
4 | Phase | Closure | PM | 2023-10-01 | 2023-10-15 | 0% | 3